## Sheet1
As an.... | I want to be able to.... | So that..... | Priority | Estimate | Sprint | Status
Developer | have an API for google maps | I can have live location services | 8 | 7 | 1 | Completed
Developer | add information from SQL | I can keep the system up to date and accurate | 9 | 6 | 1 | Completed
Developer | delete information from SQL | I can keep the system up to date and accurate | 9 | 6 | 1 | Completed
Developer | have a webpage as the main interface | its easy to access for multiple users | 9 | 7 | 1 | Completed
Developer | I can host the site on a server | customers can access the site | 9 | 7 | 1 | Completed
Developer | have an API for google maps | I can have live location services | 8 | 7 | 1 | Completed
User | sort search based on procedure | find relevant prices | 7 | 5 | 1 | Completed
User | sort search based on procedure code | so I can see results relevant to my issue | 7 | 5 | 1 | Completed
User | see the hospitals on an interactive map | I can plan a route and visualise the location | 7 | 5 | 1 | Completed
User | add location information to the app | customise my current live location | 6 | 4 | 2 | Not yet Started
Developer | update information from SQL | I can keep the system up to date and accurate | 6 | 6 | 1 | Completed
User | sort procedures from price lowest to highest/vice versa | so I can see results accurate to my budget | 6 | 6 | 2 | Not yet Started
User | restrict the search based on a input distance range | it will help me decide which hospital I need | 6 | 6 | 2 | Not yet Started
User | see live location on the interactive map | I can see hospitals in my area | 6 | 6 | 1 | Completed
User | view search results based on "best match" | I can have results tailored to me | 5 | 5 | 2 | Not yet Started
User | I can view a service providers information | Read further into the hospital | 4 | 5 | 2 | Not yet Started
User | utilize accessibility features | easily navigate and use the website | 4 | 4 | 2 | Not yet Started
User | View the site despite colour blindness | I can use the site despite colour blindness | 3 | 3 | 2 | Not yet Started
User | View the site on multiple platforms | I can access the site from mobile | 3 | 4 | 2 | Completed