## Sheet1
Sprint 2 | User Story | Task Name | Responsible | Priority | Estimate | Start | Finish | Duration(Days) | Status | Initial Points | Day 1 | Day 2 | Day 3 | Day 4
Feature 1 | 13,14 | Design a new interface for the modular, one-page application | Alfie Hippisley | 8 | 3 | 2020-02-03 | 2020-02-04 | 2 | Completed | 3 | 3 | 1 | 0 | 0
Feature 10 | 13,14 | Removal of previous maps location on the site | Ruth Carnegie | 3 | 2 | 2020-02-03 | 2020-02-03 | 1 | Completed | 2 | 2 | 0 | 0 | 0
Feature 11 | 13,14 | Removal of previous search bars location on the site | Ruth Carnegie | 2 | 1 | 2020-02-03 | 2020-02-03 | 1 | Completed | 1 | 1 | 0 | 0 | 0
Feature 12 | 13,14 | Removal of previous cards location on the site | Ruth Carnegie | 1 | 1 | 2020-02-03 | 2020-02-03 | 1 | Completed | 1 | 1 | 0 | 0 | 0
Feature 14 | 12,8 | Create UI for search filtering | Daniel Blackley | 6 | 3 | 2020-02-05 | 2020-02-06 | 1 | Completed | 3 | 3 | 3 | 2 | 1
Feature 15 | 12,8 | Creation of new one-page search display system | Marius Urbelis | 8 | 3 | 2020-02-03 | 2020-02-04 | 2 | Completed | 3 | 3 | 2 | 0 | 0
Feature 16 | 9,10 | Create scripts to transform simple maps data into SQL script | Daniel Blackley | 5 | 4 | 2020-02-04 | 2020-02-04 | 1 | Completed | 4 | 4 | 3 | 0 | 0
Feature 2 | 14,12,8 | Creation of new search bar component. | Callum Darling | 7 | 4 | 2020-02-03 | 2020-02-04 | 2 | Completed | 4 | 4 | 3 | 0 | 0
Feature 3 | 14,12,8 | Functionality of the search bar component to allow user to search dynamically | Callum Darling | 7 | 7 | 2020-02-03 | 2020-02-05 | 3 | Completed | 7 | 7 | 5 | 4 | 0
Feature 4 | 12 | Create view for price sorting of procedure | Daniel Blackley | 5 | 5 | 2020-02-04 | 2020-02-05 | 1 | Completed | 5 | 5 | 5 | 4 | 3
Feature 7 | 12 | Allow users to search based on procedure code | Ruth Carnegie | 10 | 8 | 2020-02-04 | 2020-02-06 | 3 | Completed | 8 | 8 | 8 | 5 | 3
Feature 8 | 9,10 | Implementing map into one page application. | Callum Darling | 9 | 8 | 2020-02-04 | 2020-02-06 | 2 | Completed | 8 | 8 | 8 | 7 | 5
Feature 9 | 14 | Implementing new cards into one page application. | Peter Leslie | 8 | 5 | 2020-02-04 | 2020-02-05 | 2 | Completed | 5 | 5 | 3 | 1 | 0
Feature 14 | 16 | Complete backend functionality for price sort | Daniel Blackley | 8 | 5 | 2020-02-06 | 2020-02-06 | 1 | Completed | 5 | 5 | 5 | 5 | 3
Feature 15 | 15 | Create UI for distance filtering | Marius Urbelis | 8 | 4 | 2020-02-06 | 2020-02-06 | 1 | Completed | 4 | 4 | 4 | 4 | 2
Feature 16 | 15 | Complete backend functionality for distance sort | Daniel Blackley | 8 | 5 | 2020-02-06 | 2020-02-06 | 1 | Completed | 5 | 5 | 5 | 5 | 4
[5 empty] | 68 |  |  |  |  | 68 | 68 | 55 | 37 | 21
,,