## Sheet1
User story | As an.... | I want to be able to.... | So that..... | Priority | Estimate | Sprint | Status
1 | Developer | have an API for google maps | I can have live location services | 8 | 7 | 1 | Completed
2 | Developer | add information from SQL | I can keep the system up to date and accurate | 9 | 6 | 1 | Completed
3 | Developer | delete information from SQL | I can keep the system up to date and accurate | 9 | 6 | 1 | Completed
4 | Developer | have a webpage as the main interface | its easy to access for multiple users | 9 | 7 | 1 | Completed
5 | Developer | I can host the site on a server | customers can access the site | 9 | 7 | 1 | Completed
6 | Developer | have an API for google maps | I can have live location services | 8 | 7 | 1 | Completed
7 | Developer | update information from SQL | I can keep the system up to date and accurate | 6 | 6 | 1 | Completed
8 | User | sort search based on procedure | find relevant prices | 7 | 5 | 1 | Completed
9 | User | see the hospitals on an interactive map | I can plan a route and visualise the location | 7 | 5 | 1 | Completed
10 | User | see live location on the interactive map | I can see hospitals in my area | 6 | 6 | 1 | Completed
11 | User | View the site on multiple platforms | I can access the site from mobile | 3 | 4 | 2 | Completed
12 | User | sort search based on procedure code | so I can see results relevant to my issue | 8 | 8 | 1 | Completed
13 | User | I can search for any information I require from a single entity | I can view the results in a concise and meaningful way. | 8 | 6 | 2 | Completed
14 | User | I can navigate the website from one modular page | I can easily use and navigate through the search features. | 9 | 7 | 2 | Completed
15 | User | restrict the search based on a input distance range | it will help me decide which hospital I need | 6 | 6 | 2 | In Progress
16 | User | sort procedures from price lowest to highest/vice versa | so I can see results accurate to my budget | 6 | 6 | 2 | In Progress
17 | User | utilize accessibility features | easily navigate and use the website | 4 | 4 | 2 | In Progress
18 | User | View the site despite colour blindness | I can use the site despite colour blindness | 3 | 3 | 2 | In Progress
19 | User | I can set a maximum price for procedure search | I can see options within my budget. | 5 | 6 | 2 | In Progress
20 | User | I can view a service providers information | Read further into the hospital | 4 | 5 | 2 | Not yet Started
55