## Sheet1
Sprint 2 | Task Name | Responsible | Priority | Estimate | Start | Finish | Duration(Days) | Status | Comments
Feature 1 | Design a new interface for the modular, one-page application | Alfie Hippisley | 8 | 3 | 2020-02-03 | 2020-02-04 | 2 | Completed
Feature 2 | Creation of new search bar component. | Callum Darling | 7 | 4 | 2020-02-03 | 2020-02-04 | 2 | Completed
Feature 10 | Removal of previous maps location on the site | Ruth Carnegie | 3 | 2 | 2020-02-03 | 2020-02-03 | 1 | Completed
Feature 11 | Removal of previous search bars location on the site | Ruth Carnegie | 2 | 1 | 2020-02-03 | 2020-02-03 | 1 | Completed
Feature 12 | Removal of previous cards location on the site | Ruth Carnegie | 1 | 1 | 2020-02-03 | 2020-02-03 | 1 | Completed
Feature 3 | Functionality of the search bar component to allow user to search dynamically | Callum Darling | 7 | 7 | 2020-02-03 | 2020-02-04 | 2 | Completed
Feature 7 | Allow users to search based on procedure code | Ruth Carnegie | 10 | 7 | 2020-02-04 | 2020-02-05 | 2 | Completed
Feature 15 | Creation of new one-page search display system | Marius Urbelis | 8 | 3 | 2020-02-03 | 2020-02-04 | 2 | Completed
Feature 16 | Create scripts to transform simple maps data into SQL script | Daniel Blackley | 5 | 4 | 2020-02-04 | 2020-02-04 | 1 | Completed
Feature 9 | Implementing new cards into one page application. | Peter Leslie | 8 | 5 | 2020-02-04 | 2020-02-05 | 2 | Completed
Feature 4 | Create view for price sorting of procedure | Daniel Blackley | 5 | 5 | 2020-02-04 | 2020-02-05 | 1 | Completed
Feature 8 | Implementing map into one page application. | Callum Darling | 9 | 8 | 2020-02-04 |  |  | In progress
Feature 14 | Create UI for search filtering | Daniel Blackley | 6 | 7 | 2020-02-05 |  |  | In progress
Feature 6 | Implement the functionality to allow users to compare procedure prices | Marius Urbelis | 5 | 7 |  |  |  | Not Started
Feature 13 | Restrict the search range for hospitals by a specifed distance by the user | Peter Leslie | 4 | 7 |  |  |  | Not Started
Feature 5 | Code price comparison functionality | Callum Darling | 5 | 5 |  |  |  | Not Started
76